| #### AFRICAN UNION |  | #### UNION AFRICAINE |
| --- | --- | --- |
|  |  | #### UNIÃO AFRICANA |
| ##### Addis Ababa, ETHIOPIA P. O. Box 3243 Telephone: 251 11-551 7700 Fax: 251 11-551 7844 Website: www.au.int |  |  |

DEPARTMENT OF HUMAN RESOURCES, SCIENCE AND TECHNOLOGY

ROAD MAP FOR TEACHER DEVELOPMENT

| Outputs | Activities | Tasks | Indicators and deliverables | Partners involved | Time frame |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | T1 | T2 | T3 | T4 |
| - Normative definition of the African teacher | 1.Discuss and define the profile of teachers to respond to the challenges of the 21st century | i-Identify key challenges ii-Outline of the teacher of the 21st century iii-Develop a competency framework | Profile of teachers at entry and exit point at different levels | AUC UNESCO ADEA RECs UNICEF | x | x |  |  |
|  | 2.Identify the learner’s profile in relation to education systems reforms | i-Take over the key areas of educational reforms ii-Outline of the learner of the 21st century century | Learner’s profile at entry and exit point at different levels | AUC UNESCO ADEA RECs UNICEF |  |  | x |  |
|  | 3.Develop teacher and professional development programs corresponding to updated teachers’ and learners’ profiles | i-Develop training frameworks on competencies defined ii-Develop training plans | Number of new Teacher programs comprising of innovative teaching and learning approaches | AUC UNESCO ADEA |  |  |  | x |
| - Enhanced use of Open and Distance Learning (ODL) to increase access to teacher education | 1.Advocate for increased recognition and support for prioritisation of ODL as an alternative teacher education provider | i-Make a plea for increasing number of distance education (DE) sites ii-Establish and equip these DE sites iii-Training of trainers to support learning in DE | Increase in resources allocated to ODL in Member States Increase in number of teachers trained by ODL Increase in number of ODL training centres | AUC UNESCO-IICBA ACDE AUF | x | x | x | x |
|  | 2.Develop generic frameworks for the development of appropriate teaching and learning materials | i-Train the trainers in instructional design for DE ii-Train stakeholders involved in curriculum development for DE | Manual on guidelines for curriculum development | ACDE SAQA SACMEQ |  |  | x | x |
|  | 3.Produce digital Open Educational resources (OER) | i-train other stakeholders in ODL ii. set up pedagogical teams | Increased number of OER |  |  |  |  | x |
|  | 4.Develop quality assurance standards for ODL delivery | i-define criteria for quality in DE ii- identify indicators relating to quality in DE | Quality Assurance standards document Set of agreed indicators Manual for use of indicators for data collection | ACDE OER-Africa AUF |  |  |  | x |
| - Improved performance in Science, Mathematics & Technology | 1.Develop indicators of quality for SMT teachers | i-define quality criteria in SMT | Set of agreed quality indicators for SMT | RECs ADEA, CEMASTEA |  | x |  |  |
|  | 2.Develop an African Curriculum framework for SMT teacher development | -Establish a team to develop curriculum -Identify the competences required for teaching and learning of SMT | Afrocentric SMT curricula Number of text books and teachers manuals | RECs ADEA ACDE |  | x | x | x |
|  | 3.Establish regional teacher development centers in SMT | i- Identify centers of excellence for teacher training in SMT ii- Building the capacity of these centers at infrastructure level and human resources | -Number of operational regional teacher development centers -Number of teachers trained | AUC CEMASTEA |  |  | x | x |
| - Improved teacher recruitment processes | 1.Finalise African teacher mobility protocol | i. Present the protocol to PACTED II for validation | Recruitment agencies registered with Ministries of Education and Foreign Affairs | AUC UNESCO-IICBA | x | x |  |  |
|  | 2.Advocate for teacher’s rights, welfare and their conditions of service in the host country | i- Establish, in each REC, a team for harmonization ii- Make a plea to each Member State | Improved conditions of work for teachers | RECS Member states | x | x | x | x |
|  | 3. Facilitate wider access to cross-border vacancies | i-Provide a dedicated website for member states to publish job vacancies for teachers ii- set up this site on-line iii- advertise tis website | Updated dedicated website | RECs Member states |  |  |  | x |
| - Pedagogical access to General History of Africa | - Participate in UNESCO-AU project |  | Available textbooks for primary and secondary schools | UNESCO AUC |  | x | x | x |
|  | - Develop guidelines for pre and in-service teacher education in the teaching and learning of African history | i-Identify competencies for learning general history of Africa ii-Develop guidelines for the teaching of African history | Teaching History of Africa with a hands-on approach | UNESCO AUC |  | x | x | x |
|  | - Advocate for African History as a common subject at tertiary level | i- Establish, in each REC, a team for advocacy in each Member State | More students taking History of Africa at tertiary level |  |  | x | x | x |
|  | - Identify peoples of African heritage around the world | i- Define the African Diaspora ii- Identify associations and sites for the African Diaspora iii- Dedicate a web site for e dissemination iv- promote exchange of teachers and students among the diaspora | Number of diaspora associations Number of exchanges between teachers and students of the Diaspora |  |  | x | x | x |
| - Fill the gap of policies related to the teaching profession | 1.Promote a pan-African center for training high-level executives who can influence policy issues for teachers | i- Set up in UNESCO-IICBA in Addis Ababa an Advanced Training programme aiming at developing holistic policies for the teacher ii- Present a complete course for endorsement by Member States iii- Mobilize human and financial resources for the implementation of the program | Number of African executives trained at IICBA in developing comprehensive policies for the teacher Number of policy documents holistic teacher across the continent | UNESCO ADEA COMSEC COMSEC RECs Member States Other partners | x | x | x | x |