## Dashboard
1. Financial stand |  |  |  | 2. ASEOWA Budget |  |  |  | 3. Funding/ Support Sources
[7 empty] | Donors European Union United States China, Special Fund Contribution Norway, AU Drought & Relief Partners (Technical Assistance) WHO CDC USAID IFRC UNOCHA AHA (Africa Humanitarian Action) |  | Pledges
MTN, African Development Bank
Dangote Group & Trust
Econet Wireless
Motsepe Family Trust
Stenbeck Family
Afrexim bank
Coca Cola
Vitol Group
Old Mutual Group
4.Deployed Individual Volunteers In Numbers | [8 empty] | Nedbank, Barclays Africa, Heirs Holdings
| Country |  | Numbers |  |  |  | 6. Nationalities of all current AU volunteers to ASOEWA
| Liberia |  | 33
| Sierra Leone |  | 32
| Guinea |  | 21
5. ASEOWA Volunteers deployed by Profession
7. Status of ASEOWA Secretariat Activities
[6 empty] | Activity | Deadline | Status
8. Ebola epidemic trends per affected country as at Jan 18 2015. | [5 empty] | Deployment of Head of Mission | 2014-09-01 | Completed
[6 empty] | Deployment of Dep Head of Mission | Liberia & Guinea | Completed
[6 empty] | 2nd Pre deployment training | 2014-10-09 | Completed
[5 empty] | Deployment to S/Leone and Liberia |  | 2014-10-12 | Completed
[6 empty] | Pre deployment training - Conakry | 2014-10-24 | Completed
[6 empty] | Deployment of Conakry Team | 2014-10-25 | Completed
[6 empty] | Pre deployment Briefing-Nigeria | 2014-12-03 | Completed
[6 empty] | Deployment of Nigeria Team | 2014-12-05 | Completed
[6 empty] | Predeployment Briefing-Ethiopia | 2014-12-14 | Completed
[6 empty] | Deployment of Ethiopia Team | 2014-12-16 | Completed
[6 empty] | Predeployment Briefing-DRC | 2014-12-25 | Completed
[6 empty] | Deployment of DRC Team | 2014-12-24 | Completed
[6 empty] | Predeployment Briefing- Kenya | 2014-01-08 | Completed
[6 empty] | Deployment of Kenya Team | 2014-01-10 | Completed
[6 empty] | Deployment of South Africa Team | 2015-02-13 | Planned
|  | Source: WHO http://apps.who.int/ebola/ Last viewed: 27 Jan 2015 |  |  |  | Deployment of SADR, Uganda, Namibia and Rwanda. |  | To be confirmed

## Data Tables
1.Funding |  |  |  | 2. ASEOWA Budget |  | 4. Deployed Personnel |  |  |  |  | 5. Personnel Gaps |  |  | 6.Personnel Contributing Member states
Weeks | Committed | Actual | Expenditure |  |  |  | Guinea | Liberia | Sierra Leone |  |  | Budgeted | Actual
2014-08-19 |  |  |  | Human Resources | 14117054 | Target* | 29 | 30 | 31 |  | Nurses | 30 | 8 | Uganda | 15
2014-08-26 |  |  |  | Medical | 10649633 | Actual | 0 | 27 | 21 | 48 | Public Health Officers/ Epidemiologists | 50 | 12 | Congo | 4
2014-09-02 |  |  |  | Air Transportation | 4000000 | Epidemiologist/ Public Health Officer | 0 | 9 | 3 | 12 | Medical Doctors | 100 | 11 | Burundi | 9
2014-09-09 |  |  |  | Official Travel | 2342655 | Medical Doctor | 0 | 8 | 3 | 11 | Support | 41 | 9 | Ethiopia | 7
2014-09-16 |  |  |  | Ground Transportation | 2216743 | Nurse | 0 | 5 | 3 | 8 |  | Budgeted | Actual | Tanzania | 6
2014-09-23 |  |  |  | Other Supplies, Services and Equipment | 617373 | Laboratory Technician | 0 | 1 | 5 | 6 | Pharmacists | 3 | 2 | Nigeria | 3
2014-09-30 |  |  |  | Contingencies | 328110 | Pharmacist | 0 | 0 | 2 | 2 | Social Workers | 3 |  | Rwanda | 9
2014-10-07 |  |  |  | IT | 327700 | Support | 0 | 4 | 5 | 9 | Laboratory Technicians | 8 | 6 | Kenya | 1
|  |  |  | Communications | 210232 | [5 empty] | Clinical Officers | 9 |  | Zimbabwe | 1
|  |  |  | Facility and Infrastructure | 190500 | [5 empty] | Medical Coordinator | 3
Formulas:
Weeks = [Weeks, row above]+7